## AI Register
Action Item | Assigned To | Status | Date Created | Due Date | Completion Date | Notes
arrange meeting with interpretations staff to discuss our goals and summarize Dylan/Jason's work | Suzann | In Progress | 2018-06-15 |  |  | email from Dylan 6/14/18 stating he will summarize his work with Jason
follow up with Bob Dobos and propose the CO River basin dataset for testing; set up meeting | Suzann | In Progress | 2018-06-15 |  |  | sent email to Bob on 6/13/18; ask Skye and Zamir to follow up in person
send interpretations info to group; arrange small subset to focus on interpretations and meet with interp staff | suzann | In Progress | 2018-06-18 |  |  | sent email to group on 6/19/18

## Domains
Completed | Kyle Stephens
Not Completed | Steve Campbell
See Notes | Steve Peaslee
In Progress | Kevin Godsey
Whityn Owen
Suzann Kienast
Adolfo Diaz
Unassigned
Team