## AI Register
Action Item | Assigned To | Status | Date Created | Due Date | Completion Date | Notes
arrange meeting with interpretations staff to discuss our goals and summarize Dylan/Jason's work | Suzann | See Notes | 2018-06-15 |  |  | email from Dylan 6/14/18 stating he will summarize his work with Jason
follow up with Bob Dobos and propose the CO River basin dataset for testing; set up meeting | Suzann | See Notes | 2018-06-15 |  |  | sent email to Bob on 6/13/18; ask Skye and Zamir to follow up in person; Travis, Chad, Skye, Suzann will prepare dataset and initiate conversation; email from Bob 7/26/18
send interpretations info to group; arrange small subset to focus on interpretations and meet with interp staff | Suzann | In Progress | 2018-06-18 |  |  | sent email to group on 6/19/18
explore options for stratification testing (MLRAs, ecoregions, etc) | group | In Progress | 2018-07-26 | 2018-08-07 |  | options will be discussed at 8/7/18 meeting
test MLRA stratification on upper CO River basin soil depth prediction project | Colby | In Progress | 2018-07-26
share 30m DEM developed by Rob with group (find file sharing solution) | Suzann/Rob | In Progress | 2018-07-26

## Domains
Completed | Kyle Stephens
Not Completed | Steve Campbell
See Notes | Steve Peaslee
In Progress | Kevin Godsey
Whityn Owen
Suzann Kienast
Adolfo Diaz
Unassigned
Team